# Cistercians in Yorkshire

| Issue No: | 1 |
| --- | --- |
| Issue Name: | Delay to production of Quick Time VR Movies |
| Raised By: | Nigel Williamson |
| Date: | 25th March 2002 |

## Issue Description The Digital Camera was ordered and discovered to be faulty. It was therefore returned to the suppliers for repair. The suppliers are taking considerable amount of time to respond and supply us with a working camera. Without the camera it is impossible to undertake the creation of the QuickTime VR models for Roche and Kirkstall when intended.

| ## Recommendation - Put training from CiCS in QuickTime VR on hold until the camera as been returned. - Reschedule the creation of the Roche and Kirkstall QuickTime movies. - Delay ordering of further camera equipment. - This will affect our cash flow. |  |
| --- | --- |
| Appraised by: | Sarah Foot |
| Date: | 25th March 2002 |

| ### Action | Who | When |
| --- | --- | --- |
| Hassel up camera suppliers | NPW | March - |
| Contact Paul Leman to delay training | NPW | March 2002 |
| Issue Discussed at Management Meeting | Management Board | May 2002 |
| Discuss rescheduling the shoot to the Autumn with Paul Leman is conditions in May are not suitable as the Sun will be high in the sky | NPW | May 2002 |

| ## Outcome Camera was finally returned in late April and training in the creation of movies was started. The creation of the movies has been delayed |  |
| --- | --- |
| Date Closed: |  |